## Executive Summary
Website Cybersecurity Risk Assessment
Organisation | ABC Online Services (example scenario)
Assessment basis | Assumption-based; no live system testing performed
Purpose | Identify and prioritise ten potential cybersecurity risks for a representative customer-facing website, and recommend proportionate treatments.
Preliminary candidate risks | 10
Scoring method | Likelihood (1-5) × Impact (1-5)
Risk bands | Low 1-4; Medium 5-9; High 10-16; Critical 17-25
Important limitation | Risk scores and residual estimates are illustrative planning judgements based on stated assumptions. They are not verified findings or measured probabilities. Validate them if system-specific evidence becomes available.
Next steps | Review assumptions; validate scoring rationale; refine risk owners and treatments; link the completed report and supporting evidence.
Scoring and priority | Each risk includes qualitative likelihood/impact rationale and a proposed treatment priority.

## Risk Register
Risk ID | Asset | Risk Category | Threat Event | Weakness / Exposure | Existing Controls / Assumptions | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Level | Recommended Treatment | Proposed Owner | Residual Likelihood (estimate) | Residual Impact (estimate) | Residual Score (estimate) | Residual Level (estimate) | Treatment Status | Rationale / Notes | Likelihood Rationale | Impact Rationale | Treatment Priority
R01 | Website application and database | Injection | An attacker submits crafted input that causes a database query or interpreter operation to behave unexpectedly. | Input handling or query construction may not safely separate data from commands. | Assumption: no evidence of current query protections has been supplied. Record as 'unknown/unverified', not as a confirmed absence of controls. | 4 | 5 | 20 | Critical | Use parameterised queries and safe APIs; validate inputs; review code; perform authorised security testing. | Application Development Lead | 2 | 5 | 10 | High | Proposed | Candidate risk, not a verified vulnerability. Validate secure query handling and database privileges if evidence becomes available. | Rated 4 (Likely) as a planning judgement because the website accepts user input and the effectiveness of query handling is unknown. This is not a measured probability; lower the rating if secure implementation is evidenced. | Rated 5 (Severe) because successful injection could expose, alter or destroy database records depending on privileges and data sensitivity. Confirm the actual data and database permissions. | P1 - Treat first
R02 | Customer accounts and administrative portal | Broken access control | A user accesses another user's records or performs an action outside their permissions. | Server-side authorisation checks may be missing, inconsistent or based only on client-side controls. | Assumption: role definitions and server-side authorisation controls have not been supplied. Effectiveness is unknown. | 4 | 5 | 20 | Critical | Enforce server-side authorisation on every protected operation; apply least privilege; test role and object-level access. | Application Security Lead | 2 | 5 | 10 | High | Proposed | Candidate risk, not a verified vulnerability. Validate role and object-level authorisation design. | Rated 4 (Likely) because access-control design and server-side checks are unknown in the scenario. Validate against documented roles and authorised testing before treating this as a finding. | Rated 5 (Severe) because cross-account or privileged access could expose sensitive records or enable unauthorised changes. | P1 - Treat first
R03 | Authentication and session management | Authentication failures | An attacker compromises an account through weak credentials, credential attacks or insecure session handling. | Password policy, rate limiting, multifactor authentication and session protections are unknown. | Assumption: password, MFA, rate-limiting and session controls have not been supplied. Effectiveness is unknown. | 3 | 4 | 12 | High | Use secure password storage, rate limiting, secure session cookies and session invalidation; require MFA for privileged accounts. | Identity and Access Management Owner | 2 | 4 | 8 | Medium | Proposed | Candidate risk, not a verified vulnerability. Validate authentication and session controls. | Rated 3 (Possible) because account sign-in is assumed, while rate limiting, MFA and session protections are unknown. Adjust with evidence about exposure and controls. | Rated 4 (Major) because account compromise could expose profile data or enable unauthorised actions; impact depends on account privileges and data held. | P2 - High priority
R04 | Web application and server configuration | Security misconfiguration | An attacker exploits exposed services, unsafe defaults, verbose errors or overly permissive settings. | Hardening baselines and configuration reviews may be absent or incomplete. | Assumption: hardening standards and configuration-review records have not been supplied. Effectiveness is unknown. | 3 | 4 | 12 | High | Apply secure configuration baselines; remove defaults and debug settings; restrict administration; review configurations regularly. | Infrastructure / Platform Owner | 2 | 4 | 8 | Medium | Proposed | Candidate risk, not a verified vulnerability. Validate actual deployment and configuration. | Rated 3 (Possible) because configuration details are unavailable and misconfiguration is a plausible scenario, but no specific misconfiguration has been observed. | Rated 4 (Major) because exposed services, debug information or unsafe settings could enable compromise or disruption, depending on the affected component. | P2 - High priority
R05 | Customer profile data and database | Cryptographic failures | Sensitive information is exposed because it is insufficiently protected in transit, at rest or through key management. | Encryption requirements, TLS configuration and key-management processes are unknown. | Assumption: TLS, encryption-at-rest requirements and key-management controls have not been supplied. Effectiveness is unknown. | 3 | 5 | 15 | High | Use appropriately configured TLS; protect sensitive stored data where warranted; manage keys securely; minimise retained data. | Data Protection / Security Owner | 2 | 5 | 10 | High | Proposed | Candidate risk, not a verified vulnerability. Validate data classification, encryption and key management. | Rated 3 (Possible) because encryption and key-management practices are unknown; no evidence confirms that protection is inadequate. | Rated 5 (Severe) because exposure of sensitive customer data could cause significant privacy, legal and reputational harm, depending on the data involved. | P1 - Treat first
R06 | Third-party libraries and application dependencies | Software supply chain | A vulnerable, compromised or unmaintained dependency introduces a weakness into the application. | Dependency inventory, provenance checks and patch processes may be incomplete. | Assumption: dependency inventory, trusted-source controls and patch records have not been supplied. Effectiveness is unknown. | 3 | 4 | 12 | High | Maintain a dependency inventory; use trusted sources; review advisories; update and verify dependencies; protect build pipelines. | Software Engineering Lead | 2 | 4 | 8 | Medium | Proposed | Candidate risk, not a verified vulnerability. Validate dependency inventory and patch processes. | Rated 3 (Possible) because dependency inventory and patch practices are unknown; actual likelihood depends on the software stack and advisory exposure. | Rated 4 (Major) because a vulnerable or compromised dependency could affect application integrity or availability, depending on its privileges and use. | P2 - High priority
R07 | Security logs and monitoring | Logging and alerting failures | Suspicious activity is not detected or escalated in time because relevant events are missing or alerts are ineffective. | Logging coverage, alert rules, log protection and incident ownership are unknown. | Assumption: log coverage, alerting rules, retention and incident escalation procedures have not been supplied. Effectiveness is unknown. | 3 | 4 | 12 | High | Log relevant authentication and administrative events; protect logs; configure actionable alerts; define escalation and retention. | Security Operations Owner | 2 | 3 | 6 | Medium | Proposed | Candidate risk, not a verified vulnerability. Validate monitoring coverage and response processes. | Rated 3 (Possible) because logging and alerting arrangements are unknown, so gaps are plausible but not verified. | Rated 4 (Major) because missed alerts can delay detection and response, increasing the duration or impact of another incident. | P2 - High priority
R08 | Backups and recovery processes | Availability and recovery | Data loss or a disruptive incident causes prolonged service outage because backups are missing, corrupted or not restorable. | Backup frequency, isolation, retention and restore testing are unknown. | Assumption: backup frequency, isolation, retention and restoration-test evidence have not been supplied. Effectiveness is unknown. | 3 | 4 | 12 | High | Define recovery objectives; protect and isolate backups; restrict access; monitor backup jobs; periodically test restoration. | IT Operations / Business Continuity Owner | 2 | 4 | 8 | Medium | Proposed | Candidate risk, not a verified vulnerability. Validate backup coverage, isolation, retention and restoration evidence. | Rated 3 (Possible) because backup schedules, isolation and restore testing are unknown; likelihood depends on operational practices and incident exposure. | Rated 4 (Major) because failed recovery could cause prolonged downtime or permanent data loss, depending on backup coverage and business requirements. | P2 - High priority
R09 | Website application and hosting infrastructure | Denial of service | A malicious traffic surge or resource-exhaustion attempt makes the website unavailable or significantly slower for legitimate users. | Capacity planning, rate limiting, traffic filtering and recovery arrangements are unknown. | Assumption: DDoS protections, traffic filtering, capacity monitoring and availability/recovery arrangements have not been supplied. Effectiveness is unknown. | 3 | 4 | 12 | High | Use appropriate rate limiting and traffic filtering; consider a reputable DDoS protection service; monitor availability and resource use; define incident escalation and recovery procedures. | Infrastructure / Service Operations Owner | 2 | 4 | 8 | Medium | Proposed | Candidate risk, not a verified vulnerability. Validate traffic filtering, rate limiting, capacity monitoring and availability response arrangements. | Rated 3 (Possible) because the site is assumed to be internet-facing, but traffic volume, resilience measures and threat exposure are unknown. | Rated 4 (Major) because a sustained outage could interrupt customer access and business operations; actual impact depends on service criticality and resilience. | P2 - High priority
R10 | Website transport and browser security configuration | Security headers and transport configuration | Weak transport or browser security configuration increases the chance that users are exposed to interception or certain client-side attacks. | TLS configuration, HTTPS enforcement and browser security headers are unknown or may be inconsistent. | Assumption: HTTPS enforcement, TLS settings and browser security headers have not been supplied. Effectiveness is unknown. | 3 | 3 | 9 | Medium | Enforce HTTPS and appropriately configured TLS; configure suitable security headers such as Content-Security-Policy and frame protections where appropriate; review settings against application needs and test for compatibility. | Web Platform / Application Security Owner | 2 | 3 | 6 | Medium | Proposed | Candidate risk, not a verified vulnerability. Validate HTTPS enforcement, TLS configuration and application-appropriate security headers. | Rated 3 (Possible) because HTTPS/TLS and browser security header configuration have not been supplied; this is a plausible configuration concern, not an observed weakness. | Rated 3 (Moderate) because missing or weak browser protections can increase exposure to some attacks, but impact depends on the application and other controls. | P3 - Planned improvement
Note on I1: Formula: Likelihood × Impact. Bands are defined in the Scoring Guide sheet.
Note on M1: Estimated post-treatment likelihood. Adjust only with a reasoned rationale and evidence.
Note on O1: Estimated residual score after proposed treatment; not verified unless controls are implemented and tested.

## Scoring Guide
Website Cybersecurity Risk Assessment - Scoring Guide
Purpose | Use this guide to assign consistent qualitative ratings to the example website scenario.
Likelihood | Definition | Example interpretation
1 | Rare | Would require unusual circumstances; little plausible exposure in the stated scenario.
2 | Unlikely | Possible but not expected under the stated assumptions.
3 | Possible | A credible scenario given the available information and unknown controls.
4 | Likely | A strong plausible scenario, especially where exposure is broad and controls are uncertain.
5 | Almost certain | Expected to occur repeatedly or imminently; use only with strong scenario-specific justification.
Impact | Definition | Example interpretation
1 | Negligible | Minimal disruption or data effect; readily recoverable.
2 | Minor | Limited impact affecting a small scope with straightforward recovery.
3 | Moderate | Meaningful disruption or limited data exposure requiring coordinated response.
4 | Major | Significant service interruption, sensitive data exposure or costly recovery.
5 | Severe | Extensive sensitive data exposure, major compromise or prolonged critical outage.
Score | Risk level | Treatment interpretation
1-4 | Low | Manage through routine controls and review.
5-9 | Medium | Plan proportionate treatment and monitor.
10-16 | High | Prioritise treatment and assign an accountable owner.
17-25 | Critical | Urgently review treatment options and escalate to appropriate decision-makers.
Formula | Risk score = Likelihood × Impact
Important note | These score bands and definitions are project-specific working criteria, not thresholds mandated by NIST or OWASP.
Inherent risk | Risk before considering controls.
Residual risk | Estimated risk remaining after proposed treatment. Do not describe it as verified until controls have been implemented and assessed.
Assessment basis | ABC Online Services is an example scenario. Risks and scores are illustrative, not verified findings about a live system.
Control evidence | How to record it | Do not assume a control exists or is absent without evidence. Use 'unknown/unverified' when information has not been provided.
Scoring rationale | Document why each likelihood and impact value was selected. | Explain scenario, exposure, data sensitivity, potential service impact and uncertainty. Scores are qualitative judgements, not measured probabilities.
Priority order | P1: highest urgency; P2: high priority; P3: planned improvement. | Priorities in the register are proposed for this scenario and should be reviewed by the hypothetical organisation's decision-makers.

## Asset Inventory
Asset ID | Asset | Business purpose / data | Security properties | Potential consequence if compromised
AS-01 | Customer account and profile data | Stores customer identity and profile records. | Confidentiality, integrity, privacy | Unauthorised disclosure, misuse or alteration of customer information.
AS-02 | Website application | Processes user requests and business logic. | Integrity, confidentiality, availability | Application compromise, data exposure or service disruption.
AS-03 | Authentication and session management | Controls account sign-in and session continuity. | Confidentiality, integrity | Account takeover or unauthorised actions.
AS-04 | Administrative portal and privileged accounts | Supports staff administration and configuration. | Integrity, confidentiality, availability | Privileged compromise and broad system changes.
AS-05 | Database and storage | Stores account records and application data. | Confidentiality, integrity, availability | Data theft, corruption or loss.
AS-06 | Third-party software dependencies | Libraries and components used by the application. | Integrity, availability | Introduction of vulnerable or malicious code.
AS-07 | Security logs and alerts | Supports detection, investigation and accountability. | Integrity, availability, confidentiality | Delayed detection and reduced investigation capability.
AS-08 | Backups and recovery processes | Supports restoration after accidental loss or incident. | Availability, integrity, recoverability | Prolonged outage or permanent data loss.